## Project Planner
Comprehensive Food GUI
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58
1.1 Define Project Objectives | 1 | 1 | 9 | 1 | 100%
1.2 Identify Project Stakeholders | 2 | 2 | 9 | 18 | 100%
2.1 Define Project Scope | 4 | 3 | 10 | 9 | 100%
2.2 Create WBS | 7 | 2 | 31 | 1 | 100%
2.3.1 Define and Sequence Activities | 9 | 2 | 31 | 1 | 100%
2.3.2 Estimate Activity Duration | 11 | 1 | 31 | 1 | 100%
2.4.1 Define Problem Background | 12 | 1 | 29 | 1 | 100%
2.4.2 Define System Capabilities / Overview | 13 | 2 | 29 | 1 | 100%
2.4.3 Identify the Benefits | 15 | 1 | 29 | 2 | 100%
2.5.1 Identify User Requirements | 16 | 1 |  |  | 0%
2.5.2 Identify Software Requirements | 17 | 2 |  |  | 0%
2.5.3 Identify Use Cases and Consruct Diagrams | 19 | 2 |  |  | 0%
2.6.1 Design Software | 21 | 2 |  |  | 0%
2.6.2 Identify System Components | 23 | 3 | 30 |  | 0%
2.7.1 Design the Structure | 26 | 2 |  |  | 0%
2.7.2 Design the Visuals | 28 | 2 |  |  | 0%
3.1 Implement the GUI | 30 | 3 |  |  | 0%
3.2 Implement the Food Search Feature | 33 | 3 |  |  | 0%
3.3 Implement Nutrition Breakdown Feature | 36 | 3 |  |  | 0%
3.4 Implement Nutrition Range Filter Feature | 39 | 3 |  |  | 0%
3.5 Implement Nutrition Level Filter Feature | 42 | 3 |  |  | 0%
3.6 Implement Food Wars Feature | 45 | 3 |  |  | 0%
3.7 Conduct Testing | 50 | 5 |  |  | 0%
4.1 Track Progress | 1 | Ongoing |  |  | 0%
4.2 Control Scope | 30 | Ongoing |  |  | 0%
4.3 Control Quality | 30 | Ongoing |  |  | 0%
4.4 Monitor Bugs | 30 | Ongoing |  |  | 0%
5.1 Review and Complete Work | 55 | 1 |  |  | 0%
5.2 Performance Review | 56 | 1 |  |  | 0%
5.3 Verify Completion of Work | 57 | 1 |  |  | 0%